## Blad1
When | What | Who | Hours
Sprint 1 | Discussions/Meetings | All | 64
| Mock-ups | All | 183
| Documentation | All | 20
Sprint 2 | Refining Mock-ups | Erik, Jeffrey | 68
| Discussions/Meetings | All | 86
| Studying Python | Erik, Davy, Jeffrey | 102
| Studying Django | All | 100
Sprint 3 | Programming API | Tom, Jeffrey | 64
| Html/Css Template Frontend | Davy, Jeffrey | 25
| Html/Css Template Backend | Erik | 55
| Frontend Functions | Davy, Erik, Jeffrey | 200
| Login | Jeffrey | 20
| Search Function | Erik | 40
| Refresh Search | Erik | 15
| Country Filter | Davy, Erik | 45
| Display Products/Engineers | Erik | 40
| Engineer Note | Erik | 25
| Engineer Level | Davy, Erik | 10
| Admin/Logout | Davy | 5
| Backend Functions | Erik, Davy, Tom | 226
| Display Items | Erik | 30
| Search Function | Erik | 9
| Country Filter | Davy ,Erik | 9
| API | Tom | 81
| Add Engineer | Tom | 25
| Edit Engineer | Tom | 25
| Edit Skills Engineer | Tom | 5
| Edit Note Engineer | Tom | 5
| Add Product | Tom | 5
| Edit Product | Tom | 5
| Add Category | Tom | 5
| Edit Category | Tom | 5
| Add User | Tom | 5
| Edit User | Tom | 5
| SkillMatrix/Logout | Davy | 5
| Discussions/Meetings | All | 36
| Documentation | Davy, Jeffrey, Erik | 24
Sprint 4 | Bugfixing | All | 208
| Discussions | All | 36
| Documentation | Davy, Jeffrey | 44